## Sheet1
1 | Trash icon does not load when slider is moved to closed | [2/2/2020]Unable to recreate
2 | the graph vertical scale s not adaptive | [2/2/2020]Set to occupy half screen using nested linear layouts and the android:layout_weight param
3 | Remiders are not set right if the app is minimized in the middle of a entru | [2/2/2020]added bOnPause to taskQEntryActivity
4 | check the lowest API we can actually support
5 | Allows tasks to be pre populated for when adding from who what and when tab
6 | search not working in names list
7 | sort what and who lists by count
8 | empty contact list add task on your name. Create a separate activity for it?
9 | Task types - recurring, list of tasks, geo reminder, long term tasks(random occasional popup)
10 | add option to cancel edit on a task
11 | if you save task without tags, you get a empty tags dialog afterwards and reminder time kees resetting to current time
12 | setup crash log for remote support
13 | back action - return to home as first action .
14 | add today option to home screen
15 | add close/reminder icons to dropdown
16 | StrSeparator shows up in reminders
17 | feilds reset after a tags/names dialog
18 | add preset reminder times such as morning, start of workday, end of workday, after dinner
19 | reminder of deleted tasks show up
20 | closing and reopening tags dialog doubles tags on show
21 | open via reminder when a user entry is open does not work.
22 | When we change the due date, popup a diaglog to update the todo. This is the wow factor
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78